## GiveMeARs
GIVEMEARs
Group 05: DuckyDuck |  | Project Start: | 2023-10-05
Today:
|  | Display Week: | 1 |  |  | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13 | [6 empty] | 2023-11-20 | [6 empty] | 2023-11-27 | [6 empty] | 2023-12-04 | [6 empty] | 2023-12-11 | [6 empty] | 2023-12-18 | [6 empty] | 2023-12-25 | [6 empty] | 2024-01-01
 | time axis 2023-10-02 to 2024-01-07
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | [98 empty] | Contribution Evidence | time axis 2023-10-02 to 2024-01-07
Sprint 0
Come up with ideas | Minh | 100% | 2023-10-05 | 2023-10-12 | 8
Divide the roles | Tuyên | 100% | 2023-10-05 | 2023-10-09 | 5
Write project proposal | Huyền | 100% | 2023-10-12 | 2023-10-13 | 2
Set up tools | Tuấn | 100% | 2023-10-05 | 2023-10-13
Sprint 1
Design database schema | Minh | 100% | 2023-10-14 | 2023-11-10 | 28
Design wireframe | Huyền | 100% | 2023-10-14 | 2023-10-29 | 16
Build the homepage | Tuyên | 100% | 2023-10-14 | 2023-11-04 | 22
Project Plan (PA1) | Huyền | 100% | 2023-10-14 | 2023-10-29 | 16
Planning meeting report (PA1) | Huyền | 100% | 2023-10-14 | 2023-10-29 | 16
Sprint review report (PA1) | Huyền | 100% | 2023-10-14 | 2023-10-29
Vision Document (PA1) | Tuấn | 100% | 2023-10-14 | 2023-10-29
Sprint 2
Implement the database | Minh | 50% | 2023-10-30 | 2023-11-13 | 15
Build registration and login UI | Huyền | 10% | 2023-10-30 | 2023-11-13 | 15
Build registration and login feature | Tuyên | 10% | 2023-10-30 | 2023-11-13 | 15
Build courses management feature | Tuyên | 10% | 2023-10-30 | 2023-11-13 | 15
Write use-case specification (1) | Tuyên | 100% | 2023-10-30 | 2023-11-13 | 15
Write use-case specification (2) | Huyền | 100% | 2023-10-30 | 2023-11-13
Write use-case specification (3) | Minh | 100% | 2023-10-30 | 2023-11-13
Write use-case specification (4) | Tuấn | 100% | 2023-10-30 | 2023-11-13
Revise vision document | Tuyên | 50% | 2023-10-30 | 2023-11-13
Revise project plan document | Tuyên | 100% | 2023-10-30 | 2023-11-13
Draw user case model | Tuyên | 100% | 2023-10-30 | 2023-11-13
Weekly meeting reports | Huyền | 10% | 2023-10-30 | 2023-11-13
Planning meeting report | Huyền | 10% | 2023-10-30 | 2023-11-13
Sprint review report | Huyền | 10% | 2023-10-30 | 2023-11-13
Sprint 3
Build My Course feature | Tuyên | 0% | 2023-11-14 | 2023-11-26 | 13
Build Payment and Shopping Cart feature | Minh | 0% | 2023-11-14 | 2023-11-26 | 13
Revise Use-case specification | Huyền | 0% | 2023-11-14 | 2023-11-26 | 13
Write SAD | Tuấn | 0% | 2023-11-14 | 2023-11-26 | 13
Make class diagrams | Tuấn | 0% | 2023-11-14 | 2023-11-26 | 13
Weekly meeting reports | Huyền | 0% | 2023-11-14 | 2023-11-26
Planning meeting report | Huyền | 0% | 2023-11-14 | 2023-11-26
Sprint review report | Huyền | 0% | 2023-11-14 | 2023-11-26
Phase 5 Title
Profile Management (User) feature | Minh | 0% | 2023-11-27 | 2023-12-10 | 14
Searching feature | Tuyên | 0% | 2023-11-27 | 2023-12-10 | 14
Make UI prototype | Huyền | 0% | 2023-11-27 | 2023-12-10 | 14
Prepare test plan | Tuấn | 0% | 2023-11-27 | 2023-12-10 | 14
Weekly meeting reports | Huyền | 0% | 2023-11-27 | 2023-12-10 | 14
Planning meeting report | Huyền | 0% | 2023-11-27 | 2023-12-10
Sprint review report | Huyền | 0% | 2023-11-27 | 2023-12-10
GROUP INFORMATION |  |  |  | 2018-01-13
Nguyễn Hải Tuyên | 21127474
Nguyễn Thái Huyền | 21126019
Nguyễn Trần Châu Minh | 21126030
Trần Quốc Tuấn | 21127199
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.